## Sheet1
|  | weekday |  |  | weekend
| ToDo | Student 1 | Student 2 | Student 3 | Student 1 | Student 2 | Student 3
2022-02-21 | 1. Design doc 2. Order parts 3. Design review sign-up | 1. design doc |  |  | 1. PCB board design 2. order parts
2022-02-28 | 1. PCB board reviews 2. Design Review 3. Submit first round PCB order | 1. try to collect data from IMU with Arduino Nano board (ATmega328) | 1. implement and test communications like bluetooth, i2c, and UART on Arduino Nano board | 1. design a algorithm or neural network to recognize gestures | same as in weekday | same as in weekday | same as in weekday
2022-03-07 | 1. First round PCB order due 2. Teamwork evaluation | 1. robot bluetooth communication and demo program | 1. implement and test bluetooh on PC 2. build gesture database or training dataset | 1. test the gesture recognizition program on fake or real database 2. refine and improve accuracy | same as in weekday | same as in weekday | same as in weekday
2022-03-14 |  | spring break
2022-03-21 | 1. Second round PCB order due | 1. prepare the demo program for robot | 1. help other teammates | 1. solder PCB board | combine all together and test the whole program (first round)
2022-03-28 | 1. Individual progress reports | 1. solder PCB board | 1. refinement and improvement |  | combine all together and test the whole program (second round)
2022-04-04 |  | 1. refinement and improvement |  |  | combine all together and test the whole program (third round)
2022-04-11 |  | final refinement and improvement
2022-04-18 | 1. Mock demo